## Sheet1
Hot Shoe Shuffle exibition charts
HSS Exibition Gantt chart | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Accrued Time
Pack stock | Day 1: 2 Days | 2
Move items to destination | Day 3: 1 Day | 1
Set up shop | Day 4: 2 Days | 2
Sell shoes | Day 6: 5 Days | 5
Pack up | Day 11: 2 Days | 2
| 2 days |  | 1 day |  | 2 days |  | 5 days |  | 2 days |  | Total
HSS Exibition PERT chart | Day 1: Pack stock; Day 3: Move stock; Day 5: Set up; Day 7: Sell shoes; Day 9: Pack up; Day 11: 12 days
Critical path